## Introduction
EVENT MANAGEMENT TOOLKIT
Professional Templates for Universities & Small Businesses
OVERVIEW
This workbook contains six integrated templates designed to streamline event management workflows. Each sheet serves a specific purpose
in the event lifecycle—from initial client enquiry through post-event evaluation. The templates are pre-formatted with dropdown menus,
automatic calculations, and conditional formatting to help you work efficiently. All sheets include sample data to demonstrate functionality.
Simply replace the demo data with your own information to get started.
SHEET DESCRIPTIONS
1. Event Booking Tracker
Purpose: Track all events from initial enquiry through to completion. This is your master event pipeline.
Key Features:
• Status tracking: Enquiry → Confirmed → Contract Sent → Deposit Paid → Complete (or Cancelled)
• Payment status monitoring with Overdue highlighting (red background when payment is overdue)
• Contract value tracking for revenue forecasting
2. Client Account Manager
Purpose: Lightweight CRM for managing relationships with internal departments and external clients.
Key Features:
• Contact information management (email, phone, organisation)
• Follow-up date tracking with overdue highlighting (dates in the past show in red)
• Priority levels (High/Medium/Low) and relationship owner assignment
3. Event Budget Tracker
Purpose: Detailed per-event budgeting with automatic variance calculations and forecasting.
Key Features:
• Six standard budget categories: Venue, Catering, AV/Media, Staffing, Marketing, Miscellaneous
• Automatic Variance calculation (Actual - Estimated) with colour coding
• Forecast section showing budget allocation, projected spend, and % utilisation
• Blue text indicates input cells; black text shows calculated values
4. Risk Assessment Checklist
Purpose: Comprehensive event safety and risk management checklist with automatic risk scoring.
Key Features:
• Risk Score = Likelihood × Impact (both rated 1-5, giving scores from 1-25)
• Colour-coded risk levels: Green (1-4), Amber (5-9), Orange (10-15), Red (16-25)
• Mitigation action tracking with owner assignment and status
• Reference legend included on the sheet for quick risk interpretation
5. Venue & Resource Booking
Purpose: Calendar-style booking management for multiple venues and resources.
Key Features:
• Track bookings by date, venue/room, and time slot
• Equipment requirements logging for each booking
• Status options: Available, Tentative, Confirmed, Cancelled
6. Post-Event Review
Purpose: Capture feedback, evaluate performance, and document lessons learned after each event.
Key Features:
• Attendance tracking: Expected vs Actual with variance analysis
• Budget comparison: Expected vs Actual spend
• Client satisfaction scoring (1-10 scale) and qualitative feedback capture
HOW TO USE THIS WORKBOOK
Getting Started:
1. Review each sheet to understand its purpose and layout
2. Delete the sample data rows (but keep the header row and any formulas)
3. Begin entering your own data—dropdown menus will guide valid entries
4. Use filters (already enabled) to sort and filter data as needed
Dropdown Menu Options:
• Event Status: Enquiry, Confirmed, Contract Sent, Deposit Paid, Complete, Cancelled
• Payment Status: Pending, Deposit Received, Paid in Full, Overdue, Refunded
• Client Type: Internal, External
• Priority: High, Medium, Low
• Risk Status: Open, In Progress, Mitigated, Closed
• Venue Status: Available, Tentative, Confirmed, Cancelled
Colour Coding Guide:
• Blue text = Input cells (enter your data here)
• Black text = Calculated values (formulas—do not edit)
• Red background = Overdue or requires attention
• Green background = Low risk / Complete
• Amber/Orange background = Medium-High risk / Needs review
TIPS & BEST PRACTICES
• Update the Event Booking Tracker as soon as an enquiry comes in—don't wait for confirmation
• Schedule regular reviews of the Client Account Manager to ensure follow-ups don't slip
• Create a new Budget Tracker for each major event—duplicate the sheet and rename it
• Complete the Risk Assessment at least 2 weeks before each event
• Book venues early using the Venue & Resource Booking sheet to avoid conflicts
• Complete Post-Event Reviews within 1 week of event completion while details are fresh
Version: 1.0 ¦ Last Updated: February 2026 ¦ For support, contact your administrator

## Event Booking Tracker
Event Name | Client Name | Internal/External | Enquiry Date | Event Date | Venue | Status | Contract Value | Payment Status | Notes
Annual Tech Conference 2026 | Nexus Technologies | External | 2025-11-24 | 2026-03-31 | Main Hall | Confirmed | 15000 | Deposit Received | Keynote speaker confirmed - Dr. Sarah Chen
Spring Graduate Reception | Faculty of Arts | Internal | 2025-10-20 | 2026-02-25 | Gardens & Terrace | Contract Sent | 4500 | Pending | Awaiting Dean's signature on contract
Leadership Workshop Series | Bright Futures Foundation | External | 2025-11-10 | 2026-01-28 | Conference Room A | Deposit Paid | 8500 | Deposit Received | 6 sessions over 3 months
Summer Music Festival | Student Union | Internal | 2025-09-30 | 2026-05-31 | Outdoor Space | Confirmed | 12000 | Paid in Full | 3 stages, 15 acts confirmed
Corporate Training Day | Meridian Consulting | External | 2025-12-05 | 2025-12-31 | Training Room | Complete | 3200 | Paid in Full | Excellent feedback - rebooking for Q3
Alumni Networking Dinner | Alumni Association | Internal | 2025-08-31 | 2025-11-29 | Main Hall | Complete | 7500 | Overdue | URGENT: Invoice sent 3x, escalate to finance
Product Launch - TechStart | TechStart Inc. | External | 2025-12-19 | 2026-03-04 | Main Hall + Foyer | Enquiry | 22000 | Pending | High-value prospect - follow up by Friday
Board Strategy Retreat | University Executive | Internal | 2025-11-17 | 2026-01-13 | Boardroom | Cancelled | 0 | Refunded | Postponed to next quarter

## Client Account Manager
Client Name | Organisation | Type | Email | Phone | Last Contact Date | Next Follow-Up | Relationship Owner | Priority | Notes
James Morrison | Nexus Technologies | External | j.morrison@nexustech.com | (555) 234-5678 | 2025-12-29 | 2026-01-28 | Sarah Johnson | High | Key account - annual conference worth $15K+
Prof. Emily Watson | Faculty of Arts | Internal | e.watson@university.edu | Ext. 4521 | 2025-12-24 | 2026-01-08 | Michael Chen | Medium | Graduate reception planning in progress
Rachel Green | Bright Futures Foundation | External | rachel@brightfutures.org | (555) 876-5432 | 2025-11-29 | 2025-12-04 | Sarah Johnson | High | OVERDUE: Workshop series - needs session 4 details
Tom Richards | Student Union | Internal | t.richards@su.university.edu | Ext. 2200 | 2025-12-27 | 2026-02-27 | Michael Chen | Medium | Music festival coordination
Diana Patel | Meridian Consulting | External | d.patel@meridianconsulting.com | (555) 321-9876 | 2025-12-31 | 2026-02-07 | Sarah Johnson | Medium | Interested in Q3 training programme
Dr. Robert Huang | Alumni Association | Internal | r.huang@alumni.university.edu | Ext. 3100 | 2025-10-30 | 2025-11-19 | Michael Chen | High | OVERDUE: Chase payment for networking dinner
Marcus Webb | TechStart Inc. | External | marcus.webb@techstart.io | (555) 999-1234 | 2025-12-19 | 2026-01-03 | Sarah Johnson | High | New lead - $22K product launch opportunity
Linda Martinez | Local Business Network | External | linda@localbiznet.com | (555) 444-7890 | 2025-11-09 | 2026-03-19 | Michael Chen | Low | Exploratory - may need venue for AGM

## Event Budget Tracker
EVENT BUDGET TRACKER
Event Name: | Annual Tech Conference 2026
Event Date: | 2026-03-31
Category | Description | Estimated Cost | Actual Cost | Variance
Venue | Main Hall rental + setup | 3500 | 3500 | 0
Catering | Lunch + refreshments (150 pax) | 4500 | 4875 | 375
AV/Media | Projector, screens, microphones | 1200 | 1200 | 0
Staffing | Event coordinators + security | 2000 | 2200 | 200
Marketing | Printed materials + signage | 800 | 650 | -150
Miscellaneous | Parking, contingency | 500 | 325 | -175
TOTAL |  | 12500 | 12750 | 250
FORECAST SECTION
Total Budget Allocated: | 15000
Estimated Total Spend: | 12500
Projected Remaining: | 2500
% of Budget Used: | 83.33%

## Risk Assessment Checklist
Risk Category | Description | Likelihood (1-5) | Impact (1-5) | Risk Score | Mitigation Action | Owner | Status | RISK SCORE KEY
Health & Safety | General attendee safety, first aid provision | 2 | 4 | 8 | First aid station on-site, trained staff | Sarah Johnson | Mitigated | 1-4 (Low) | Monitor
Fire Safety | Emergency evacuation procedures | 1 | 5 | 5 | Fire marshal briefed, exits clearly marked | Facilities Team | Mitigated | 5-9 (Medium) | Action Required
Crowd Control | Managing 150+ attendees during breaks | 3 | 3 | 9 | Staggered break times, multiple refreshment points | Michael Chen | In Progress | 10-15 (High) | Priority Action
Weather | Outdoor registration area exposed | 3 | 2 | 6 | Marquee on standby, indoor backup option | Sarah Johnson | Mitigated | 16-25 (Critical) | Immediate Action
Technical Failure | AV equipment malfunction during keynote | 2 | 4 | 8 | Backup laptop, spare projector on-site | AV Technician | In Progress
Vendor No-Show | Catering company fails to deliver | 1 | 5 | 5 | Confirmed booking, backup caterer identified | Sarah Johnson | Mitigated
Security | Unauthorised access, theft of equipment | 2 | 3 | 6 | Badge system, security guard at entrance | Security Team | Mitigated
Food Safety | Allergic reactions, food poisoning | 2 | 4 | 8 | Allergen info collected, labelled food stations | Catering Lead | Open
Speaker Cancellation | Keynote speaker unable to attend | 2 | 5 | 10 | Backup speaker identified, remote option available | Michael Chen | In Progress
Data/Privacy | Attendee data breach, GDPR compliance | 1 | 5 | 5 | Encrypted registration, minimal data collection | IT Security | Mitigated

## Venue & Resource Booking
Date | Venue/Room | Time Slot | Event Name | Booked By | Equipment Required | Status
2025-12-31 | Main Hall | 09:00-17:00 | Corporate Training Day | Diana Patel | Projector, 50 chairs, 10 tables | Confirmed
2025-12-31 | Conference Room A | 09:00-12:00 | Leadership Workshop - Session 4 | Rachel Green | Whiteboard, flipchart, 20 chairs | Confirmed
2025-12-31 | Boardroom | 14:00-16:00 | Budget Review Meeting | Finance Team | Video conferencing | Confirmed
2026-01-28 | Conference Room A | 09:00-12:00 | Leadership Workshop - Session 5 | Rachel Green | Whiteboard, flipchart, 20 chairs | Tentative
2026-02-25 | Gardens & Terrace | 16:00-21:00 | Spring Graduate Reception | Prof. Emily Watson | Marquee, lighting, PA system, catering setup | Tentative
2026-03-04 | Main Hall + Foyer | All Day | Product Launch - TechStart | Marcus Webb | Stage, AV system, demo stations, catering | Tentative
2026-03-31 | Main Hall | 08:00-18:00 | Annual Tech Conference 2026 | James Morrison | Full AV, 150 chairs, registration desk, signage | Confirmed
2026-03-31 | Conference Room A | 08:00-18:00 | Tech Conference - Breakout Room 1 | James Morrison | Projector, 30 chairs, networking tables | Confirmed
2026-03-31 | Conference Room B | 08:00-18:00 | Tech Conference - Breakout Room 2 | James Morrison | Projector, 30 chairs, workshop supplies | Confirmed
2026-05-31 | Outdoor Space | 12:00-22:00 | Summer Music Festival | Tom Richards | 3 stages, full PA, lighting rigs, generators | Confirmed
2026-01-03 | Training Room | 09:00-13:00 |  |  |  | Available
2026-01-03 | Boardroom | All Day |  |  |  | Available

## Post-Event Review
Event Name | Event Date | Expected Attendance | Actual Attendance | Expected Budget | Actual Budget | Client Satisfaction (1-10) | Key Successes | Areas for Improvement | Follow-Up Actions
Corporate Training Day | 2025-12-31 | 45 | 48 | 3200 | 3150 | 9 | Excellent facilitator, engaging content, good catering | Room was slightly warm - check AC next time | Send follow-up survey; discuss Q3 booking
Alumni Networking Dinner | 2025-11-29 | 120 | 98 | 7500 | 7200 | 7 | Good speaker lineup, venue looked great | Lower turnout than expected; parking issues | Chase outstanding payment; improve RSVP tracking
Winter Graduation Ceremony | 2025-09-12 | 500 | 485 | 15000 | 14800 | 10 | Smooth ceremony, excellent photography, emotional speeches | Queue management at entrance could be better | Book same photographer for summer; add queue barriers
Startup Pitch Competition | 2025-08-11 | 80 | 95 | 5000 | 5400 | 8 | High energy, great sponsors, good media coverage | Ran 30 mins over schedule; judges needed briefing | Create judge briefing pack; build in buffer time